## Use Case Template
Project Title: VolunteerSync Release #: 4.0 Sprint #: 8 | [9 empty] | Color Key | Green = Done in Milestone 3 | Blue = Done in Milestone 4 | Orange = Partially implemented | Red = Currently out of scope due to ongoing adjustments (rows hidden)
User Stories (Functional and Non-Functional)
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate Hours | Actual Hours | Priority | % Complete | Milestone # Completed in: |  | Total estimated hours: | 195
A1 | Admin | As an admin | I would like to approve or reject organizations | so that only valid groups can post events. | 3 | 2 | Must Have | 100% | 3 |  | Actual Hours: | 121
A2 | Admin | As an admin | I would like to manage user roles | so that I can control access across the platform. | 2 | 3 | Must Have | 100% | 3
A3 | Admin | As an admin | I would like to deactivate inappropriate or inactive events | so that I can keep the catalog clean. | 2 | 1 | Should Have | 100% | 3 |  | User stories Complete: | 58
A4 | Admin | As an admin | I would like to review audit logs | so that I can monitor suspicious or unauthorized activity. | 2 | 1 | Should Have | 100% | 4 |  | User stories remaining: | 14
A6 | Admin | As an admin | I would like to configure system-wide settings | so that I can adjust default behaviors. |  |  | Nice to Have
A7 | Admin | As an admin | I would like to generate platform-wide reports | so that I can see overall volunteer engagement. | 6 | 3 | Nice to Have | 100% | 4 |  | Estimated hours remaining: | 54
A8 | Admin | As an admin | I would like to manage tags and categories | so that event classification stays consistent. | 1 | 1 | Nice to Have | 100% | 4
O1 | Organizer / Event Management | As an organizer | I would like to create, edit, publish, cancel, and archive events with capacity | so that I can manage opportunities. | 6 | 4 | Must Have | 100% | 3 |  | Percent user stories remaining based on estimated hours: | 27.69%
O2 | Organizer / Event Management | As an organizer | I would like to view and manage sign ups | so that I know how many volunteers to expect. | 2 | 2 | Must Have | 100% | 3
O3 | Organizer / Event Management | As an organizer | I would like to mark volunteer attendance and completion | so that hours can be awarded. | 3 | 2 | Must Have | 100% | 3 |  | Percent user stories complete: | 81.67%
O4 | Organizer / Event Management | As an organizer | I would like to generate signed PDF certificates with verification IDs | so that volunteers have proof of service. | 5 | 3 | Must Have | 100% | 3
O5 | Organizer / Event Management | As an organizer | I want an analytics dashboard with attendance rates, hours awarded, and top volunteers | so that I can measure success. | 6 | 5 | Must Have | 100% | 3
O6 | Organizer / Event Management | As an organizer | I would like to export event data as CSV | so that I can share reports with my organization. | 3 | 1 | Should Have | 100% | 4 |  | Percent user stories completed in Milestone 3 | 38.16%
O7 | Organizer / Event Management | As an organizer | I would like to clone previous events | so that I can quickly schedule recurring opportunities. | 1 | 1 | Should Have | 100% | 4
O8 | Organizer / Event Management | As an organizer | I would like to tag events with categories (e.g., environment, education) | so that volunteers can search more effectively. | 2 | 1 | Should Have | 100% | 4 |  | Percent user stories completed in Milestone 4 | 38.16%
O9 | Organizer / Event Management | As an organizer | I would like to message registered volunteers before an event | so that I can share updates or instructions. | 4 |  | Nice to Have | 0%
O10 | Organizer / Event Management | As an organizer | I would like to upload event images | so that my postings look more engaging. |  |  | Should Have
O12 | Organizer / Event Management | As an organizer | I would like to restrict sign ups based on age or physical requirements | so that volunteers meet event needs. | 1 | 1 | Should Have | 100% | 4 |  | Percent user stories completed in Milestone 5 | 0%
O13 | Organizer / Event Management | As an organizer | I would like to manage waitlists when capacity is reached | so that more volunteers can be included if space opens. | 2 |  | Nice to Have | 0%
O14 | Organizer / Event Management | As an organizer | I would like to receive notifications when volunteers withdraw | so that I can adjust staffing. | 1 | 1 | Nice to Have | 100% | 4
O15 | Organizer / Event Management | As an organizer | I would like to reply to volunteer reviews | so that I can address concerns or show appreciation. | 2 |  | Nice to Have | 0% |  |  | Number of user stories completed in Milestone 3 | 29
V1 | Volunteer Experience | As a volunteer | I would like to register and log in | so that I can access my dashboard. | 2 | 2 | Must Have | 100% | 3
V2 | Volunteer Experience | As a volunteer | I would like to update my profile with interested tags | so that events can be recommended to me. | 1 | 1 | Nice to Have | 100% | 4 |  | Number of user stories completed in Milestone 4 | 29
V3 | Volunteer Experience | As a volunteer | I would like to search and filter events by date, location, tags, and organizer | so that I can find the right fit. | 3 | 2 | Must Have | 100% | 3
V4 | Volunteer Experience | As a volunteer | I would like to sign up for events and withdraw before the deadline | so that I can manage my commitments. | 1 | 1 | Must Have | 100% | 3 |  | Number of user stories completed in Milestone 5 | 0
V5 | Volunteer Experience | As a volunteer | I would like to receive email reminders | so that I don’t forget events. | 4 | 5 | Must Have | 100% | 4
V6 | Volunteer Experience | As a volunteer | I want a dashboard showing my hours, certificates, and upcoming events | so that I can track my activity. | 5 | 5 | Must Have | 100% | 3
V7 | Volunteer Experience | As a volunteer | I would like to download my certificates as PDFs | so that I can share them with schools or employers. | 3 | 2 | Must Have | 100% | 3
V8 | Volunteer Experience | As a volunteer | I would like to follow specific organizers or event categories | so that I get notified when new opportunities match my interests. | 2 | 1 | Should Have | 100% | 4
V9 | Volunteer Experience | As a volunteer | I would like to rate and review events | so that others know about the quality of the experience. | 4 |  | Nice to Have | 0%
V10 | Volunteer Experience | As a volunteer | I would like to see my volunteering history and milestones | so that I can reflect on my impact. | 5 | 4 | Should Have | 80%
V11 | Volunteer Experience | As a volunteer | I would like to filter events that match my availability | so that I don’t waste time reviewing conflicts. | 1 | 1 | Should Have | 100% | 3
V12 | Volunteer Experience | As a volunteer | I would like to view organizer ratings | so that I can choose reliable opportunities. | 3 |  | Nice to Have | 0%
V13 | Volunteer Experience | As a volunteer | I would like to receive a summary of my volunteering hours | so that I can stay motivated. | 5 | 4 | Nice to Have | 100% | 4
V14 | Volunteer Experience | As a volunteer | I would like to earn badges or milestones for certain volunteering achievements | so that I feel rewarded. | 4 |  | Nice to Have | 0%
V15 | Volunteer Experience | As a volunteer | I would like to bookmark or save interesting events | so that I can revisit them later. | 2 |  | Nice to Have | 0%
V16 | Volunteer Experience | As a volunteer | I would like to receive alerts when a waitlisted spot opens | so that I can claim it. | 2 |  | Nice to Have | 0%
V17 | Volunteer Experience | As a volunteer | I would like to message an organizer directly through the platform | so that I can ask questions. | 3 |  | Nice to Have | 0%
S1 | System Operations / Infrastructure | As the system | I would like to enforce role-based access | so that each user only sees features appropriate to their role. | 4 | 4 | Must Have | 100% | 3
S2 | System Operations / Infrastructure | As the system | I would like to prevent duplicate sign ups and enforce event capacity | so that data stays consistent. | 2 | 1 | Must Have | 100% | 3
S3 | System Operations / Infrastructure | As the system | I would like to generate unique verification IDs for each certificate | so that authenticity can be confirmed. | 1 | 2 | Must Have | 100% | 3
S4 | System Operations / Infrastructure | As the system | I would like to provide a public verification page | so that third parties can check certificate validity. | 2 | 2 | Must Have | 100% | 3
S5 | System Operations / Infrastructure | As the system | I would like to log key actions like event creation, sign up, and certificate issuance | so that there is an audit trail. | 2 | 2 | Must Have | 100% | 3
S6 | System Operations / Infrastructure | As the system | I would like to send queued email notifications | so that reminders are reliable. | 4 | 4 | Should Have | 100% | 4
S10 | System Operations / Infrastructure | As the system | I would like to archive past events | so that searches only return upcoming opportunities. | 2 | 1 | Should Have | 100% | 4
S11 | System Operations / Infrastructure | As the system | I would like to automatically expire events after their end date | so that data stays current. | 2 | 1 | Should Have | 100% | 3
S12 | System Operations / Infrastructure | As the system | I would like to calculate and display top volunteers for an organizer | so that recognition is encouraged. | 2 | 2 | Should Have | 100% | 4
S13 | System Operations / Infrastructure | As the system | I would like to anonymize volunteer data in reports | so that privacy is respected. | 2 | 2 | Nice to Have | 100% | 4
S14 | System Operations / Infrastructure | As the system | I would like to provide export options (CSV, PDF) for dashboards | so that data can be shared externally. | 3 | 3 | Should Have | 100% | 4
S16 | System Operations / Infrastructure | As the system | I would like to store all timestamps in UTC | so that event scheduling is consistent across time zones. | 1 | 1 | Nice to Have | 100% | 4
S17 | System Operations / Infrastructure | As the system | I would like to throttle excessive API requests | so that performance is not impacted by misuse. | 3 | 2 | Nice to Have | 100% | 4
S18 | System Operations / Infrastructure | As the system | I would like to provide search suggestions as volunteers type | so that finding events is faster. | 5 |  | Nice to Have | 0%
S19 | System Operations / Infrastructure | As the system | I would like to generate audit logs for certificate verifications | so that third-party lookups are tracked. | 1 | 1 | Nice to Have | 100% | 4
NFR1 | Performance | As the system | I would like to respond to event searches within 2 seconds | so that volunteers can quickly find opportunities. | 1 | 1 | Must Have | 100% | 3
NFR2 | Performance | As the system | I would like to support at least 500 concurrent users | so that the platform remains stable under load. | 1 | 1 | Must Have | 100% | 4
NFR3 | Security | As the system | I want all passwords to be salted and hashed using bcrypt | so that user credentials remain secure. | 1 | 1 | Must Have | 100% | 3
NFR4 | Security | As the system | I want all traffic to be encrypted with HTTPS | so that data transmitted is secure. | 1 | 1 | Must Have | 100% | 3
NFR5 | Security | As the system | I would like to sanitize and validate all inputs | so that injection attacks are prevented. | 2 | 1 | Must Have | 100% | 3
NFR6 | Usability | As the system | I would like to be fully functional on desktop, tablet, and mobile | so that all users can access it. | 4 | 4 | Should Have | 100% | 3
NFR7 | Usability | As the system | I would like to comply with WCAG 2.1 accessibility guidelines | so that users with disabilities can participate. |  |  | Should Have
NFR8 | Maintainability | As the system | I would like to log all database CRUD operations | so that administrators can audit activity. | 2 | 2 | Should Have | 100% | 4
NFR9 | Maintainability | As the system | I want automated tests for core features | so that changes do not introduce regressions. | 4 |  | Should Have | 0%
NFR10 | Maintainability | As the system | I would like to provide a staging environment | so that updates can be tested before release. | 1 | 1 | Should Have | 100% | 4
NFR11 | Reliability | As the system | I would like to back up the database daily | so that data is not lost in case of failure. | 1 | 1 | Should Have | 100% | 4
NFR12 | Reliability | As the system | I would like to recover from failures gracefully with clear error messages | so that users are not confused. | 2 | 2 | Should Have | 100% | 4
NFR14 | Scalability | As the system | I would like to separate frontend, backend, and database layers | so that the architecture is modular and maintainable. | 3 | 3 | Nice to Have | 100% | 3
NFR15 | Extensibility | As the system | I would like to support multiple languages in the future | so that the platform can serve diverse communities. | 10 |  | Nice to Have | 0%
NFR16 | Reliability | As the system | I would like to provide consistent error handling patterns across both frontend and backend | users receive predictable and non-frustrating feedback when something goes wrong. | 2 | 2 | Must Have | 100% | 4
NFR18 | Maintainability | As the system | I would like to centralize exception logging with error codes tied to documentation | developers can quickly trace failure points and resolve bugs faster. | 2 | 2 | Should Have | 100% | 4
NFR19 | Performance | As the system | I would like to generate PDF certificates within 1 second for standard cases | certificate issuance doesn’t block normal workflow. | 1 | 1 | Should Have | 100% | 3
NFR20 | Security / Trust | As the system | I would like to cryptographically store certificate verification hashes with non reversible values | third parties can trust certificates without exposing internal data. | 1 | 1 | Must Have | 100% | 3
NFR21 | Security / Privacy | As the system | I would like to practice data minimization by only storing information needed to operate the service | sensitive personal data surface area stays limited and ethical. | 1 | 1 | Must Have | 100% | 3
NFR22 | Monitoring / Observability | As the system | I would like to track key metrics | reporting dashboards are meaningful and data driven. | 5 | 5 | Should Have | 100% | 4
NFR23 | Scalability | As the system | I would like API endpoints to support pagination and filtering | large lists do not degrade performance as the system grows. |  |  | Should Have
NFR24 | Ethics / Accessibility | As the system | I would like to notify users when major policy or privacy handling behavior changes occur | trust and transparency are maintained. | 2 | 3 | Nice to Have | 100% | 4
NFR25 | Extensibility | As the system | I would like to support pluggable notification channels such as SMS in the future | communication options can grow as partners need. | 8 |  | Nice to Have | 0%